## 12 Week MVP Plan
Week | Target | Difficulty
2022-10-03 | Requiremet gathering and finalization | Easy
2022-10-10 | WebApp Module 1 complete | Medium
2022-10-17 | WebApp Module 2 complete | Medium
2022-10-24 | WebApp Module 3 complete | Medium
2022-10-31 | WebApp Module 4 complete | Medium
2022-11-07 | Infrastructure Readiness(Makefile,yml file, Requirements.txt etc) | Complex
2022-11-14 | CI Completion | Complex
2022-11-21 | CD Completion | Complex
2022-11-28 | Unit Testing | Medium
2022-05-12 | Buffer time for adhoc issue fix | Easy
2022-05-12 | QA Handover | Medium
2022-05-19 | Prod Deployment | Complex
Goals
Demo on Every Monday
Sprint Planning on Every Tuesday

## Quarterly Plan
Timeline | Release Plan
Q4 2022 | API Web App v1 Production
Q1 2023 | API Web App v1.1 Production
Q2 2023 | API Web App v2 Production
Q3 2023 | API Web App v2.1 Production
Q4 2023 | API Web App v3 Production

## Yearly Plan
Yearly Plan : By Q4 2023, we're expecting WebAPp v3 Major release goLive